Assignment 1:

Team Working Agreement & Board Setup

Client: Northstar Retail Co.
Sprint: Northstar Sprint (1-Week Engagement)
Team Pod: Group 112
Published Team Repository/Space: [https://github.com/Maxie-07/PLP--Northstar-sprint-group-112]

Team Roles & Context

- Maxwell Opio (UX & Content Writer)

- Daisy Lopez Adhiambo (No-Code Workflow Specialist)

- Onzere weyne Onzere (Data & QA Specialist)

- Abdiaziz (Scrum & Documentation Lead)

- Tshidi Malope (Audit & Go-Live Readiness Coordinator)

MVP Scope: Support Deflection for Order Status and Returns & Refunds.
Technical Approach: No-code self-service decision-tree prototype (Google Forms for customer flow, Google Sheets for demonstration/testing data).

- Team Charter

- Communication Rules

  - All work-related communication must occur in the team's shared channel or repository space to ensure progress is visible to all members.

  - Any blocker, delay, or risk must be communicated immediately upon identification.

  - Task-related communication must reference the specific Task ID where applicable.

  - Updates on task progress must be posted on the same day the work occurs.

- Deadline Rules

- The sprint runs for exactly one week.

- All assigned board tasks must be completed within the sprint period.

- If a team member identifies a risk to completing assigned work, they must notify the team on the same day.

- Work must not be intentionally delayed until the end of the sprint.

- Conflict-Resolution Rules

- Disagreements must be raised directly and promptly with the involved team members.

- If unresolved between the individuals, the issue must be raised to the full team for a decision.

- All final decisions must be documented in the Decision Log within the team space.

- Task Ownership & Granularity

- Every task on the Project Board must have exactly one assigned owner.

- The owner is responsible for moving the task's status and confirming its Definition of Done is met.

- Anti-black-box rule: No board task may represent more than 4 hours of work.

- Tasks exceeding 4 hours must be split until the Definition of Done is a single checkable sentence. Broad, black-box tasks are strictly prohibited.

- Board Status Discipline

- The Project Board must reflect the current state of the team’s work at all times.

- Board status must be updated on the exact same day the work is completed.

- Batch-updating accumulated task statuses at the end of the week is prohibited.

- Commit/Edit Convention

All commits and edits in the repository/space must strictly follow this format:
    <type>: <what changed> - <why it matters>

Vague or incomplete messages are explicitly unacceptable, specifically:

- wip

- updates

- Zero-Activity Escalation

Zero visible activity for 2 or more days triggers this Charter's escalation path immediately:

- The team member with no visible activity must be contacted directly on the same day the 2-day threshold is reached.

- If no response or update follows, the issue must be raised to the full team immediately to reassign work and protect the sprint deadline.

- Peer Reliability Index

- The Peer Reliability Index is strictly confidential.

- It must never be shared verbatim between teammates.

- Only aggregate patterns may be released.

- Charter Sign-Off

| Team Member | Role | Signature | Date |
| --- | --- | --- | --- |
| Maxwell Opio | UX & Content Writer | MO | 11/08/2026 |
| Daisy Lopez Adhiambo | No-Code Workflow Specialist | DLA | 11/08/2026 |
| Onzere Weyne Onzere | Data & QA Specialist | OWO | 11/08/2026 |
| Abdiaziz Suleiman Muhamed | Scrum & Documentation Lead | ASM | 11/08/2026 |
| Tshidi Malope | Audit & Go-Live Readiness Coordinator | TM | 11/08/2026 |

- Project Board

Note: All tasks are strictly scoped to comply with the <4 hour anti-black-box rule.

| Task ID | Task | Owner | Priority | Definition of Done |
| --- | --- | --- | --- | --- |
| TASK-01 | Create published team repository and link workspace assets | Maxwell Opio | High | Repository is live and Google Forms/Sheets are linked in the README. |
| TASK-02 | Document MVP scope and technical approach in repository | Abdiaziz | High | Target categories and the no-code approach are formally recorded in the repo. |
| TASK-03 | Draft Charter sections: Communication & Deadlines | Maxwell Opio | High | Communication and deadline rules are written in the shared Team Charter. |
| TASK-04 | Draft Charter sections: Conflict Resolution & Escalation | Tshidi Malope | High | Conflict and zero-activity escalation rules are written in the Charter. |
| TASK-05 | Draft Charter sections: Granularity, DoD, & Commits | Abdiaziz | High | Granularity, DoD, and commit conventions are written in the Charter. |
| TASK-06 | Map decision-tree logic and form questions for Order Status | Maxwell Opio | High | Logic and questions for the Order Status category are mapped in the design doc. |
| TASK-07 | Map decision-tree logic and form questions for Returns & Refunds | Abdiaziz | High | Logic and questions for the Returns & Refunds category are mapped in the design doc. |
| TASK-08 | Build Google Form for Order Status flow | Daisy Lopez Adhiambo | High | Form is live, functional, and follows the mapped decision-tree logic. |
| TASK-09 | Build Google Form for Returns & Refunds flow | Daisy Lopez Adhiambo | High | Form is live, functional, and follows the mapped decision-tree logic. |
| TASK-10 | Setup Google Sheet for demonstration and testing data | Onzere weyne Onzere | High | Sheets are populated with sample order and return data for QA testing. |
| TASK-11 | Define test cases for Order Status flow | Onzere weyne Onzere | High | Test cases for Order Status are documented in the repository space. |
| TASK-12 | Define test cases for Returns & Refunds flow | Onzere weyne Onzere | High | Test cases for Returns are documented in the repository space. |
| TASK-13 | Initialize Decision Log and record technical approach decision | Daisy Lopez Adhiambo | High | Decision Log document is created and the first entry is committed to the repo. |
| TASK-14 | Circulate Charter for sign-off and publish final artifacts | Tshidi Malope | High | Charter is signed by all members and uploaded to the published repository. |
| TASK-15 | Draft 1-page go-live readiness note | Tshidi Malope | High | Go-live note documents what works, what is known-broken, and what Northstar needs to pick it up. |

- Compliance Check

| Requirement / Evaluation Criterion | Status | Evidence |
| --- | --- | --- |
| Clarity and specificity of team norms (25%) | Met | Charter explicitly defines rules for Communication, Deadlines, Conflict, Commits, and Escalation. |
| Task breakdown granularity (50%) | Met | 14 granular tasks on the board. No black-box tasks. Implementation is bounded to specific builds and logic mapping. |
| Tool setup correctness (25%) | Met | TASK-01 and TASK-14 establish the published repository/space. Board contains exactly the 5 required fields. |
| Signed Team Charter requirement | Met | Sign-off table included with all 5 team members and specific roles. |
| Minimum 10 tasks | Met | Project Board contains 15 specific tasks. |
| Owner on every task | Met | Every task has one named team member assigned based on pod roles. |
| Priority on every task | Met | Every task has an assigned priority. |
| Definition of Done on every task | Met | Every task has exactly one checkable Definition of Done sentence. |
| Maximum 4-hour task rule | Met | Anti-black-box rule stated in Section 4; all tasks scoped to fit the limit. |
| Correct commit/edit convention | Met | Section 6 defines the exact format and explicitly bans unacceptable messages. |
| Same-day board status | Met | Section 5 explicitly mandates same-day status movement. |
| 2+ day zero-activity escalation | Met | Section 7 defines the immediate escalation trigger and path. |
| Peer Reliability confidentiality | Met | Section 8 explicitly states it is confidential and never shared verbatim. |