## Audit Log
Timestamp | Team Member | Task ID | Commit / Edit Log Entry | Artifact Link / Location
2026-08-10 09:30 | Prototype Design Lead | TSK-01 | setup: initialize Google Form and branching structure - establishes baseline support deflection workspace. | Google Form -Section 1.
2026-08-10 11:15 | Charter Lead | TSK-02 | docs: draft order-status decision-tree paths - outlines questions to route order tracking inquiries without human intervention | Google Docs / Flowchart
2026-08-10 14:00 | QA & Testing Results Lead | TSK-03 | feat: create mock order dataset - provides 5 order records for testing self-serve lookup responses | Google Sheets - Orders Tab
2026-08-11 10:00 | Audit & Documentation Lead | TSK-04 | setup: configure master audit log sheet - establishes traceability for team contributions and process discipline | Master Audit Log Sheet
2026-08-11 13:30 | Prototype Design Lead | TSK-05 | feat: build section branching logic for order-status flow - automatically redirects customers based on order selection | Google Form - Section 2
2026-08-11 15:45 | Charter Lead | TSK-06 | docs: add return/refund policy guidance section - answers common refund timelines directly in form | Google Form - Section 3
2026-08-12 09:15 | QA & Testing Results Lead | TSK-07 | feat: populate stock availability dataset - adds inventory status for 5 SKUs to support stock queries | Google Sheets - Inventory Tab
2026-08-12 11:30 | Prototype Design Lead | TSK-08 | fix: resolve incorrect branching route in stock query section - ensures customers land on correct stock response | Google Form - Section 4
2026-08-13 14:00 | Audit & Documentation Lead | TSK-10 | audit: execute Day 4 mid-sprint contribution review - verifies task-to-edit log balance across all members | Master Audit Log Sheet
2026-08-14 10:00 | Audit & Documentation Lead | TSK-09 | docs: draft 1-page go-live readiness note - documents working features and handoff steps for Northstar team | Google Docs - Handoff Note

## Contribution Mapping
Team Member Role | Task IDs Assigned | Total Est. Hours | Primary Responsibilities / Deliverables
Prototype Design Lead | TSK-01, TSK-05, TSK-08 | 3.5 hrs | Initialize form structure, build branching logic, and fix routing bugs.
Charter Lead | TSK-02, TSK-06 | 3.0 hrs | Map decision-tree flow paths and write return/refund guidance content.
QA & Testing Results Lead | TSK-03, TSK-07 | 3.0 hrs | Build mock order tracking and stock availability datasets in Sheets.
Audit & Documentation Lead | TSK-04, TSK-09, TSK-10 | 4.0 hrs | Set up audit log, perform Day 4 audit check, and draft Go-Live Readiness Note.
Project Leader & Board Lead | Sprint Governance | 2.5 hrs | Oversee project board, facilitate team handoffs, and ensure deadline compliance.